LabelHub Data Annotation Platform

Project Implementation Plan

A full-lifecycle Web annotation platform covering data production, AI pre-review, human review, and multi-format export

Version: V1.2 (Revised for Test Data Adaptation and Multimodal Capability Retention)
Prepared on: 2026-05-21

0. Document Overview and Table of Contents

This plan is prepared based on the LabelHub Data Annotation Platform AI Full-Stack Project Requirements. Its purpose is to convert the assignment requirements into an executable development plan, module breakdown, technical route, schedule, testing approach, and delivery standards.

| Section | Content |
| --- | --- |
| 1 | Project objectives, scope, and acceptance criteria |
| 2 | Roles, permissions, and end-to-end business process |
| 3 | Overall architecture and technology selection |
| 4 | Implementation plan for core modules |
| 5 | Data model, API, and state machine design |
| 6 | Development schedule, milestones, and responsibility allocation |
| 7 | Testing, deployment, delivery, and risk control |
| 8 | Appendix: key schemas, APIs, and demo script recommendations |

Implementation principle First ensure that the three main tracks are fully runnable: the dynamic form architecture, the workflow state machine, and the AI review Agent. Other materials, dashboards, mobile adaptation, and similar capabilities should be added progressively as enhancements.

1. Project Objectives, Scope, and Acceptance Criteria

1.1 Construction Objectives

Build a demonstrable, deployable, and extensible LabelHub Web data annotation platform.

Implement a complete closed loop from task creation, template building, task publishing, annotation, AI automated pre-review, human review, to multi-format export.

Establish a serializable annotation Schema system so that the same template can be edited and previewed in the Designer and rendered at runtime in the Labeler workspace.

Use asynchronous queues and structured LLM outputs to create an AI quality-inspection Agent that is traceable, retryable, and supported by human fallback.

Use a clear state machine and audit logs to ensure data consistency, accountability, and review explainability in multi-user collaboration scenarios.

1.2 MVP Scope

| Scope Item | Required for MVP | Enhancement |
| --- | --- | --- |
| Roles and permissions | Owner, Labeler, Reviewer, and System Agent account perspectives; RBAC permission control | Organization, team, and tenant isolation |
| Task management | Task CRUD, draft/published/paused/ended states, quota, deadline, and first-come-first-served claiming | Assignment, quota-based order grabbing, and complex reward rules |
| Dataset management | JSON/JSONL/Excel import, item preview, batch editing; field recognition for qa_quality and preference_compare; complete retention of raw_payload, media_type, media_url, and content_markdown. | Data cleaning rules, duplicate detection, remote media availability checks, and media metadata extraction |
| Template building | Drag-and-drop materials, property panel, Schema saving and versioning, runtime rendering by Renderer; core materials retained: ShowItem, text, single choice, multiple choice, tags, JSON, LLM, and file/image upload. | Multiple tabs, advanced linkage, custom function sandbox, video upload transcoding, and direct multimodal model parsing |
| Annotation workspace | Task marketplace, claiming, answering, drafts, submission validation, and returned-item modification | Offline cache and mobile adaptation |
| AI pre-review | Prompt templates, scoring dimensions, asynchronous queue, structured output, retry, and visible results | Multi-model routing, batch evaluation, and score calibration |
| Human review | Initial review/re-review/final review process, return/pass/revise, batch operations, and audit logs | Sampling strategy and dual-reviewer consistency evaluation |
| Export | JSON, JSONL, CSV, and Excel; asynchronous export and download history | Reusable field-mapping templates and export job scheduling |

1.3 Acceptance Criteria

| Dimension | Acceptance Standard | Corresponding Implementation |
| --- | --- | --- |
| Functional completeness | The Owner can complete task creation, template building, publishing, result viewing, and export. The Labeler can claim tasks, answer, submit, view returned items, and modify them. AI pre-review results are visible and traceable. Exported files can be consumed downstream. | End-to-end demo + automated tests + exported sample files |
| Engineering quality | Clear module boundaries, complete type constraints, unit and integration tests for key processes, and complete README and deployment documentation. | Monorepo, layered architecture, CI testing, and OpenAPI documentation |
| Product experience | No obvious stutter in key paths, friendly error messages, draft loss prevention, and good display at both 1280x800 and 1920x1080. | UI review, E2E tests, and responsive layout checks |

1.4 Test Data Adaptation and Multimodal Retention Principles

1.4.1 Test Dataset Analysis

| Dataset | Record Count | Main Fields | Media/Type Distribution | Platform Requirements |
| --- | --- | --- | --- | --- |
| qa_quality | 30 | id, category, difficulty, lang, media_type, media_url, content_markdown, prompt, model_answer, reference, tags, expected_dimensions | text 20; image 4; video 3; markdown 3 | Support Q&A quality scoring, media asset display, Markdown rich-text rendering, dimension-based scoring, and return reasons. |
| preference_compare | 12 | id, task_type, lang, prompt, response_a, response_b, model_a, model_b, preferred, margin, dimensions, safety_flag, annotator_note | 12 text-based preference-comparison records; covering knowledge Q&A, code, summarization, translation, creative writing, mathematical reasoning, multi-turn dialogue, and safety compliance. | Support side-by-side A/B display, preference decision, strength margin, multi-dimensional tags, safety risk, and rationale. |
| Excel/JSON/JSONL | Three input formats | The same dataset exists in json, jsonl, and excel directories | The import formats vary, but the business fields are consistent | The import layer must perform format parsing and field standardization; export must continue to support JSON/JSONL/CSV/Excel. |

1.4.2 Specific Adjustments to the Implementation Plan

| Adjustment Item | Plan Revision | Implemented In |
| --- | --- | --- |
| Data import | The importer identifies qa_quality and preference_compare by dataset type; preserves the complete raw_payload fields; does not trim media_type, media_url, or content_markdown. | backend/dataset, backend/import, frontend/preview |
| Item rendering | ShowItem is extended into four read-only display types: text/image/video/markdown. Text is displayed directly, images are previewed, videos are played with a video player, and Markdown is rendered safely with embedded media handling. | frontend/modules/schema/renderer, frontend/pages/labeler |
| Annotation template | File upload and image upload materials are retained. In the current text-heavy dataset, they are mainly used for evidence assets, exception screenshots, and supplementary attachments; future multimodal tasks can reuse them directly. | frontend/modules/schema/materials, backend/file |
| Storage design | MySQL stores tasks and annotation records. Media URLs and attachment metadata are persisted. File bodies use a local volume, MinIO, or object storage. Redis is used for upload rate limiting, temporary state, and asynchronous tasks. | backend/file, infra/docker-compose |
| AI Agent | Prompt input includes not only text fields but also media_type, media_url, and content_markdown. For media items, the MVP first passes media links and human-visible content as context, with later extension to multimodal models. | agent/prompts, agent/llm, backend/review |

Implementation adjustment conclusion: the current test data mainly focuses on Q&A quality evaluation and preference comparison, but the qa_quality dataset already includes image, video, and markdown media source data. Therefore, even if the current sample stage is mostly text-based, the platform design must not remove image/file upload, media display, or Markdown rich-text rendering capabilities. The MVP should retain the basic loop of media display plus evidence attachment upload. Complex video transcoding, asset review, and advanced object-storage governance should be advanced as enhancements.

2. Roles, Permissions, and Business Process

2.1 Role and Permission Model

| Role | Key Capabilities | Core Pages / Interfaces |
| --- | --- | --- |
| Task Owner | Create tasks, configure templates, import items, configure review Prompts and scoring dimensions, publish/pause/end tasks, view results, and export data | Task management, template builder, review configuration, data acceptance, export center |
| Labeler | Browse task marketplace, claim tasks, answer online, save drafts, submit answers, view return reasons, and modify returned items | Task marketplace, annotation workspace, my contributions |
| Human Reviewer | View AI pre-review results, perform initial review/re-review/final review, return/pass/revise, and batch operations | Review workspace and review result list |
| AI Review Agent System | Listen to submission queues, call the LLM for scoring, write back AI comments and decisions, retry failures, and provide human fallback | Background Worker, review records, and task logs |

2.2 End-to-End Main Process

Owner creates a task -> Imports the dataset -> Builds the annotation template by drag-and-drop and publishes the Schema version -> Configures the AI review Prompt and scoring dimensions -> Publishes the task Labeler browses the task marketplace -> Claims an item -> Answers online based on the Schema and auto-saves the draft -> Submits the answer System Agent performs automated pre-review -> Success: writes dimension scores and recommendations -> Failure: retries, and transfers to human review after the threshold is exceeded Reviewer performs human review -> Pass: enters the accepted/exportable state -> Return: Labeler modifies and resubmits Owner exports data -> Selects field mapping and format -> Generates files asynchronously -> Download history is available

3. Overall Architecture and Technology Selection

3.1 Overall Architecture

| Layer | Component | Responsibility |
| --- | --- | --- |
| Frontend application layer | React 18 + TypeScript + Ant Design + Formily + dnd-kit Note: the frontend UI component library uniformly adopts Ant Design and does not adopt Semi Design. The Owner, Labeler, and Reviewer portals share one design specification. | Owner console, Labeler workspace, Reviewer review console, template Designer and Renderer |
| API service layer | Java 17/21 + Spring Boot 3 + Spring Security + Spring Web + Spring Validation + Spring Data JPA/MyBatis-Plus + OpenAPI/Swagger Responsibilities: authentication and authorization, task/dataset/template/review/export APIs, state-machine transaction control, and audit logs. | Authentication and authorization, task/dataset/template/review/export APIs, and state-machine transaction control |
| Asynchronous task layer | Redis + Spring Task/Scheduler + Redisson/Redis Stream + MySQL job table Responsibilities: AI pre-review queue, import jobs, export jobs, failure retry, and idempotency control. Key tasks are persisted in the MySQL job table, while Redis handles queues, locks, cache, and rate limiting. | AI pre-review queue, import jobs, export jobs, failure retry, and idempotency control |
| AI Agent layer | OpenAI-Compatible LLM Client + Prompt Renderer + Function Calling/JSON Schema structured output parser Responsibilities: connect to any model service compatible with OpenAI Chat Completions/Responses through base_url, api_key, and model configuration; generate Prompts by task configuration and parse structured scoring results. | Generate Prompts by task configuration, call the model, parse structured results, and write back scores and recommendations |
| Data layer | MySQL + Redis + optional object storage/local file storage MySQL stores core business data such as tasks, Schemas, items, submissions, reviews, and export records. Redis is used for cache, distributed locks, asynchronous queues, draft debounce state, and rate limiting. | Structured business data, locks and cache, file uploads, and export file storage |
| Engineering layer | Docker Compose, GitHub Actions, JUnit 5/Spring Boot Test, Vitest, Playwright, OpenAPI/Swagger, Postman/Apifox Used for local startup, automated testing, API documentation, deployment, and demo environment delivery. | Local startup, testing, deployment, documentation, and demo environment delivery |

3.2 Recommended Repository Structure

labelhub/ ├── frontend/ # React + TypeScript + Ant Design frontend project │ ├── src/pages/owner/ # Owner console: tasks, templates, review config, export │ ├── src/pages/labeler/ # Labeler workspace: task marketplace, answering, my contributions │ ├── src/pages/reviewer/ # Reviewer workspace: AI results, human review, batch operations │ └── src/modules/schema/ # Designer/Renderer, material registry, Schema validation ├── backend/ # Java Spring Boot backend API service │ ├── src/main/java/.../auth │ ├── src/main/java/.../task │ ├── src/main/java/.../schema │ ├── src/main/java/.../annotation │ ├── src/main/java/.../review │ ├── src/main/java/.../export │ └── src/main/resources/db/migration ├── agent/ # AI review Agent as an independent service or module │ ├── prompts/ # Prompt templates and scoring-dimension configuration │ ├── src/main/java/.../llm # OpenAI-compatible LLM Client │ ├── src/main/java/.../jobs # AI pre-review queue, retry, idempotency, writeback │ └── src/main/java/.../parser # JSON Schema / Function Calling output parser ├── infra/ │ ├── docker-compose.yml # MySQL / Redis / backend / agent / frontend / nginx │ ├── nginx.conf │ └── env.example ├── docs/ │ ├── architecture.md │ ├── api-docs.md │ ├── state-machine.md │ └── demo-script.md └── submission/ ├── README.md ├── screenshots/ ├── api-docs/ └── demo-video.md

4. Implementation Plan for Core Modules

4.1 Owner Console

| Submodule | Functions | Implementation Points |
| --- | --- | --- |
| Task management | Title, description, rich-text instructions, tags, reward rules, deadline, quota; draft/publish/pause/end. | All state transitions go through the state-machine service. Before publishing, validate whether the dataset, Schema, and review rules are complete. |
| Dataset management | JSON, JSONL, and Excel import; batch editing; item preview; qa_quality/preference_compare field standardization; retention of media_type, media_url, and content_markdown. | Import runs asynchronously. Row-level errors are returned. Original items are stored in raw_payload. Media files are not forcibly downloaded; they are rendered safely by URL/Markdown first, while uploaded attachments are stored separately in file_assets. |
| Template builder | Left material panel, middle canvas, right property panel; Schema save/preview/publish; includes text, enum, JSON, LLM, file/image upload, and ShowItem multimedia display. | The material registry is decoupled from the renderer. Save draft_schema and publish versioned_schema. |
| Review configuration | Prompt templates, scoring dimensions, pass/return thresholds, and human-review conditions. | Prompts use variable rendering. Output structure is constrained by JSON Schema. |
| Dashboard and export | Progress, pass rate, return rate, AI average score, and export records. | Dashboards use aggregate queries. Export runs through background jobs and saves download history. |

4.2 Dynamic Form Designer / Renderer

This module is the first core difficulty of the project. The implementation uses a material registry, Schema DSL, and runtime interpretation by the Renderer to ensure that template-building output is serializable, versionable, and replayable.

| Design Item | Solution |
| --- | --- |
| Material registration | Each material includes type, label, defaultProps, propertySchema, renderComponent, validator, and exportMapper. |
| Schema storage | The schema_versions table stores JSON Schema, version number, status, publisher, and publishing time. After a task is published, it references only a fixed version. |
| Designer | The left material panel is rendered from the registry. After dragging into the canvas, a fieldId is generated. The right property panel reads propertySchema to render configuration items automatically. |
| Renderer | At runtime, the Renderer reads the schema and recursively renders layout/components. ShowItem is read-only; input materials collect answers. |
| Validation system | Required, length, regex, enum, JSON format, and cross-field conditional validation. Before submission, execute validate(schema, answers, item.raw_payload) uniformly. |
| Field linkage | Describe conditions through visibleWhen, requiredWhen, disabledWhen, and validateWhen. Avoid storing uncontrolled functions in the database. |
| LLM component | The component configures promptTemplate, inputMapping, outputMapping, and triggerMode. Results are used as reference or prefill and do not directly overwrite human answers. |
| Media ShowItem | ShowItem selects the renderer according to raw_payload.media_type: text renders text, image uses a preview component, video uses an HTML5 player, and markdown uses safe Markdown rendering while handling embedded images/videos. |
| Upload materials retained | Even if the current samples mainly collect text judgments, image upload and file upload are retained for evidence screenshots, exception attachments, and future multimodal expansion. Upload results only save file_id/URL/metadata into the answer. |

Schema example

{ "schemaVersion": "1.0.0", "layout": { "type": "vertical", "children": ["raw_title", "category", "ai_hint", "answer"] }, "fields": { "raw_title": { "type": "ShowItem", "label": "Original Title", "source": "raw_payload.title" }, "category": { "type": "Select", "label": "Topic Category", "required": true, "options": ["Digital Products", "Home", "Apparel", "Other"] }, "ai_hint": { "type": "LLMAssist", "label": "AI Annotation Suggestion", "promptTemplateId": "prompt_product_category_v1", "inputMapping": { "title": "raw_payload.title" }, "outputMapping": { "suggestion": "category" } }, "answer": { "type": "Textarea", "label": "Annotation Notes", "required": true, "maxLength": 500 } } }

4.3 Labeler Workspace

| Page / Capability | Functions | Key Implementation |
| --- | --- | --- |
| Task marketplace | Task search, filters, task cards, and claim entry. | Only published and unexpired tasks are displayed. Quota and concurrent claims use database transactions or Redis locks. |
| Answering page | Item navigation, previous/next/skip, template rendering, and submission validation. | The Renderer renders according to schemaVersion. Drafts are saved when switching items. ShowItem displays text/image/video/markdown raw items, while upload materials collect evidence attachments. |
| Draft auto-save | Scheduled save, save on page leave, and network-error prompts. | Frontend debounce, backend draft upsert, and local cache fallback. |
| Returned-item modification | Display previous review comments, AI comments, and diff comparison. | Each submission generates annotation_revision. Review comments are associated with the revision. |
| My contributions | Statistics and lists for submitted, passed, returned, and pending-modification items. | Aggregate submission and review states by user. |

4.4 AI Automated Pre-Review Agent

The AI Agent is implemented through a background asynchronous queue. After the Labeler submits an answer, an ai_review_job is created immediately. The Worker consumes the job, calls the LLM, and writes back scores and decisions using structured output.

| Stage | Implementation Plan |
| --- | --- |
| Enqueue | After successful submission, write submission and ai_review_job in the same transaction. job_key = submission_id + schema_version + prompt_version to guarantee idempotency. |
| Prompt rendering | Read prompt_template and scoring_dimensions from task review configuration, inject the original item, annotation answer, and template field definitions. For qa_quality media items, keep media_type, media_url, and content_markdown as Prompt context. LLM requests go uniformly through the OpenAI-compatible Client. |
| Structured output | Require the model to output dimension scores, total score, risk_flags, decision, comment, and evidence through Function Calling or JSON Schema constraints. The backend validates with JSON Schema plus Jackson/Bean Validation. Validation failure enters retry or human review. |
| Decision rules | If total score >= threshold and there are no high-risk flags, AI passes. If below the rejection threshold, return or request human review. The middle interval enters human review. |
| Failure retry | Network, rate-limit, and parsing failures retry 3 times. If still failing, mark NEED_HUMAN_REVIEW and record the error summary. |
| Audit traceability | Save prompt_version, model, base_url identifier, temperature, request_hash, response_json, token_usage, latency, and error-stack summary to ensure AI results are explainable, traceable, and reviewable. |

AIReviewResult = { "scores": { "relevance": 86, "accuracy": 82, "format_compliance": 95, "safety": 100 }, "total_score": 90, "decision": "PASS ¦ REJECT ¦ NEED_HUMAN_REVIEW", "comment": "Conclusion and revision suggestions", "risk_flags": ["format_warning"], "evidence": ["The category field matches the original title", "The answer field format is compliant"] }

4.5 Multi-Role Human Review Flow

| State | Description | Operator Role | Next State |
| --- | --- | --- | --- |
| DRAFT | Annotation draft, not submitted | Labeler | SUBMITTED |
| SUBMITTED | Submitted by Labeler and waiting for AI enqueue | System | AI_REVIEWING |
| AI_REVIEWING | AI Agent is processing | System | AI_PASSED / AI_REJECTED / NEED_HUMAN_REVIEW |
| AI_PASSED | AI passes and enters human re-review | Reviewer | HUMAN_REVIEWING |
| AI_REJECTED | AI clearly marks it as unqualified | Reviewer or rule | RETURNED / NEED_HUMAN_REVIEW |
| HUMAN_REVIEWING | Human initial review, re-review, or final review in progress | Reviewer | APPROVED / RETURNED / REVISED |
| RETURNED | Returned to Labeler for modification | Labeler | DRAFT / RESUBMITTED |
| APPROVED | Final review passed and data is accepted into storage | Owner/System | EXPORTABLE |
| EXPORTABLE | Eligible for export | Owner | EXPORTED |

Audit requirement All state transitions must be written to audit_logs: operator_id, role, from_state, to_state, reason, snapshot, and created_at. Return operations must include a reason, and the Labeler can view the previous round of comments in the workspace.

4.6 Multi-Format Export

| Capability | Implementation Plan |
| --- | --- |
| Format support | Support JSON, JSONL, CSV, and Excel. Export content includes original items, annotation answers, AI review records, and human review records, selectable through field mapping. |
| Asynchronous export | After export_job is created, job_id is returned immediately. The Worker generates the file and uploads it to MinIO/S3. The frontend polls progress or receives notifications through SSE/WebSocket. |
| Field mapping | The Owner can select fields, rename fields, and choose whether to include review records. The mapping configuration is saved as export_mapping. |
| Download history | Record exporter, task, format, row count, status, file size, and expiration time. On failure, display an error summary. |

5. Data Model, API, and State Machine Design

5.1 Core Data Model

| Table Name | Key Fields | Description |
| --- | --- | --- |
| users | id, name, email, password_hash, status | Basic user information |
| roles / user_roles | role_code, permissions | RBAC permission model |
| tasks | id, title, desc, status, owner_id, quota, deadline, reward_rule | Task master table |
| task_schema_versions | id, task_id, version, schema_json, status, created_by, published_at | Template version table, immutable after publishing |
| datasets | id, task_id, file_id, import_status, total_count, error_count | Dataset import record |
| items | id, task_id, dataset_id, raw_payload, item_status | Items to be annotated |
| assignments | id, task_id, item_id, labeler_id, status, locked_until | Item claiming/distribution record |
| annotations | id, assignment_id, schema_version_id, answer_json, status, revision_no | Annotation answer and version |
| drafts | id, assignment_id, answer_json, updated_at | Draft auto-save |
| ai_review_jobs | id, annotation_id, job_key, status, retry_count, error_summary | AI review queue job |
| ai_review_results | id, job_id, scores_json, decision, comment, prompt_snapshot, response_json | AI scoring result |
| human_reviews | id, annotation_id, reviewer_id, round_no, decision, reason, diff_json | Human review record |
| audit_logs | id, entity_type, entity_id, operator_id, action, before_json, after_json, created_at | Audit log |
| export_jobs | id, task_id, format, mapping_json, status, progress, file_id | Export job |
| files | id, storage_key, filename, mime_type, size, checksum | Uploaded files and exported files |
| file_assets | id, owner_id, storage_type, object_key, url, mime_type, size, checksum, created_at | Metadata table for uploaded attachments/images/future video assets. File bodies are stored in local volume, MinIO, or cloud object storage. |
| dataset_import_profiles | id, dataset_type, field_mapping_json, media_strategy, created_at | Stores import-mapping rules for qa_quality, preference_compare, and similar datasets to avoid hard-coded import logic. |

5.2 API Groups

| API Group | Representative Endpoints |
| --- | --- |
| Authentication and users | POST /auth/login; GET /users/me; GET /permissions |
| Task management | POST /tasks; GET /tasks; PATCH /tasks/{id}; POST /tasks/{id}/publish; POST /tasks/{id}/pause |
| Dataset | POST /tasks/{id}/datasets/import; GET /datasets/{id}/items; PATCH /items/{id} |
| Template | POST /tasks/{id}/schemas/draft; POST /schemas/{id}/publish; GET /schemas/{versionId} |
| Claiming and answering | GET /market/tasks; POST /tasks/{id}/claim; PUT /assignments/{id}/draft; POST /assignments/{id}/submit |
| AI review | GET /ai-review/jobs; POST /ai-review/jobs/{id}/retry; GET /ai-review/results/{annotationId} |
| Human review | GET /review/tasks; POST /review/{annotationId}/approve; POST /review/{annotationId}/reject; POST /review/batch |
| Export | POST /tasks/{id}/exports; GET /exports; GET /exports/{id}/download |
| Files and media | POST /files/upload; GET /files/{id}; GET /media/proxy?url=; POST /datasets/{id}/import-profiles |

5.3 Concurrency and Consistency Strategy

Task claiming: create a unique constraint on task_id + item_id. During claiming, check quota and item_status within a transaction to avoid duplicate claims.

Task publishing: validate task basic information, dataset, schema_version, and review configuration. After success, freeze the Schema version.

Annotation submission: validate assignment ownership, schemaVersion, and draft version. Keep annotation and ai_review_job writes consistent within one transaction.

AI review idempotency: use a unique constraint on job_key. If the job is consumed repeatedly, directly return the existing result.

Review operation: human review uses an optimistic-lock version field to prevent multiple Reviewers from overwriting the same record concurrently.

Export: only APPROVED/EXPORTABLE data is exported. Export jobs save query conditions and field-mapping snapshots to ensure reproducible results.

6. Development Schedule, Milestones, and Responsibility Allocation

6.1 Two-Week Implementation Schedule

| Phase | Period | Key Tasks | Milestone Deliverables |
| --- | --- | --- | --- |
| Phase 1: Basic architecture | Week 1 | Repository setup, Docker Compose, MySQL/Redis data model, Spring Boot authentication/RBAC, frontend Ant Design basic routing, UI framework. | The three directories frontend/backend/agent can start; users can log in and enter different pages by role; database migration scripts are executable. |
| Phase 2: Tasks and datasets | Week 1 | Task CRUD, state machine, qa_quality/preference_compare dataset import, item preview, retention of media_type field, first-come-first-served claiming. | Owner can import JSON/JSONL/Excel; text, image, video, and Markdown raw items can be previewed; Labeler can see and claim tasks. |
| Phase 3: Dynamic forms | Week 1 | Material registry, Designer drag-and-drop, property panel, Schema saving, Renderer rendering, validation, media ShowItem, file/image upload materials. | Complete core materials: text, single choice, multiple choice, tags, JSON, ShowItem, LLM, file/image upload; media items can be displayed read-only. |
| Phase 4: Annotation and drafts | Week 2 | Answering page, item navigation, draft auto-save, submission validation, and returned-item modification. | Labeler can claim tasks, answer, submit, and modify after return. |
| Phase 5: AI and human review | Week 2 | AI review queue, Prompt configuration, structured output, retry, Reviewer console, and audit logs. | After submission, AI pre-review runs automatically; Reviewer can view scores and pass/return. |
| Phase 6: Export and delivery | Week 2 | Multi-format export, download history, dashboard, tests, deployment, README, and demo video script. | Complete end-to-end demo, deployment environment, and submission directory. |

6.2 Suggested Responsibility Allocation

| Role | Responsibilities |
| --- | --- |
| Frontend lead | Three-role routing, UI specification, task management, Designer/Renderer, annotation workspace, review console, and export center. |
| Backend lead | Java Spring Boot data model, APIs, RBAC, state machine, import/export, transaction consistency, audit logs, and MySQL/Redis integration. |
| AI/Agent lead | OpenAI-compatible LLM client, review Prompt, scoring dimensions, structured output parsing, queue retry, Agent monitoring, and result writeback. |
| Testing/delivery lead | Unit tests, integration tests, E2E tests, Docker deployment, README, API documentation, and demo video script. |

7. Testing, Deployment, Delivery, and Risk Control

7.1 Test Plan

| Test Type | Coverage | Tools / Methods |
| --- | --- | --- |
| Unit tests | Schema validator, state-machine transitions, export field mapping, Prompt rendering, and LLM output parsing. | JUnit 5 / Spring Boot Test / Mockito; frontend uses Vitest. |
| Integration tests | Complete API chain for task publishing, data import, claiming and submission, AI enqueue, review, and export. | Spring Boot Test + Testcontainers (MySQL/Redis) + test database migration scripts. |
| E2E tests | Owner creates a task, builds a template, and publishes; Labeler claims, answers, and submits; Reviewer reviews; Owner exports. | Playwright. |
| Performance and stability | Large-form rendering, batch import, export jobs, AI retry, and concurrent claiming. | JMeter/k6 load-test scripts + Spring Actuator metrics + application logs. |
| Compatibility tests | 1280x800 and 1920x1080; Chrome/Edge. | Manual walkthrough + screenshot comparison. |
| Dataset compatibility tests | JSON/JSONL/Excel import, field mapping, media-field retention, ShowItem rendering, and export field consistency for qa_quality and preference_compare. | Sample-data regression tests + Spring Boot integration tests + Playwright page verification. |

7.2 Deployment Plan

| Environment | Configuration |
| --- | --- |
| Local development | Docker Compose starts MySQL, Redis, and optional file storage. Frontend: npm run dev. Backend: ./mvnw spring-boot:run. Agent starts as an independent Spring Boot Worker/Service. |
| Demo environment | Cloud server with at least 2C4G. Nginx reverse proxy. frontend/backend/agent containerized deployment. MySQL and Redis can use self-hosted containers or managed cloud instances. File uploads and exported files can use local volume, MinIO, or cloud object storage. |
| Configuration management | Environment variables manage MYSQL_URL, MYSQL_USERNAME, MYSQL_PASSWORD, REDIS_URL, LLM_BASE_URL, LLM_API_KEY, LLM_MODEL, and FILE_STORAGE_TYPE. Sensitive information must not be committed to the repository. |
| Logging and monitoring | Spring Boot API request logs, Agent Worker job logs, AI call logs, and export failure logs. Key errors can display summaries in the console; Actuator/Prometheus can be integrated if necessary. |

7.3 Delivery Checklist

Source repository: frontend + backend + Agent, using a Monorepo.

README.md: architecture description, module breakdown, local startup guide, key design trade-offs, and environment-variable description.

Demo video: 5-10 minutes, covering the complete flow of Owner, Labeler, and Reviewer roles.

Related documents: architecture diagram, key technical points, state-machine explanation, Demo screenshots, AI Coding process records, and basic technical documentation.

Demo environment description: deployment URL, test accounts, account roles, and notes.

API documentation: OpenAPI/Swagger, Postman Collection, or Markdown documentation.

Test data and exported samples: cover both qa_quality and preference_compare datasets; include at least JSON, JSONL, CSV, and Excel export samples; verify that media fields and attachment fields are not lost.

7.4 Risks and Responses

| Risk | Impact | Response Strategy |
| --- | --- | --- |
| Dynamic form scope expansion | Slows overall progress and affects main-chain acceptance. | Complete the seven required materials and basic linkage first; advanced materials enter the enhancement backlog. |
| Schema-change compatibility difficulties | Historical answers cannot be rendered or reviewed correctly. | Freeze schema_version after task publishing. Changes generate a new version. Answer records bind to a specific version. |
| Unstable AI output | Parsing failures or unexplainable scoring. | Use OpenAI-compatible structured output, JSON Schema/Jackson validation, failure retry, and human-review fallback. Save Prompt and response snapshots for review. |
| Duplicate concurrent claiming | The same item is claimed by multiple people or quota is oversold. | Database unique constraints + transaction checks + optimistic locking / Redis lock. |
| Inconsistent export data | Downstream consumption fails. | Export only final-approved data. Validate field mapping. Save export job snapshots and sample validation. |
| Unstable demo environment | Affects final presentation. | Prepare a local Docker fallback environment, recorded demo video, and fixed test accounts. |
| Weakening multimodal capability because samples are text-heavy | Future image, video, or Markdown tasks require rework and would conflict with the original material requirements. | MVP retains media ShowItem, file/image upload, attachment metadata, and optional object storage. Complex video transcoding and multimodal model parsing are enhancement items. |

8. Appendix: Demo Script and Priority Recommendations

8.1 Presentation Demo Script

Owner logs in, creates the "Product Quality Cleaning v3" task, and fills in title, description, quota, and deadline.

Owner imports qa_quality / preference_compare items in JSON, JSONL, or Excel format, displays field mapping and import statistics, and previews text, image, video, and Markdown raw items.

Owner enters the template builder, drags in ShowItem, single choice, multiple choice, text, JSON, file/image upload, and LLM assist components, configures required fields, validation rules, and media display method, then saves and publishes the Schema.

Owner configures AI review Prompt, scoring dimensions, and thresholds, then publishes the task.

Labeler logs in to the task marketplace, searches for the task, claims an item, enters the answering page, uses LLM assistance, auto-saves the draft, and submits the answer.

The system enters AI automated pre-review and displays dimension scores, total score, decision, AI comments, and original Prompt snapshot.

Reviewer logs in to the review console, views AI results and the round 1/2 diff, then passes or returns the item.

Labeler views the return reason, modifies the answer, and resubmits.

After final approval by the Reviewer, the Owner selects field mapping in the export center, exports JSONL and Excel asynchronously, and checks download history.

8.2 Development Priorities

| Priority | Functions | Reason |
| --- | --- | --- |
| P0 | Authentication/RBAC, task state machine, data import, template Schema, Renderer, media ShowItem, file/image upload, annotation submission, AI queue, human review, and export. | Required for main-chain acceptance and must be fully runnable. |
| P1 | Designer drag-and-drop experience, field linkage, batch review, download history, dashboard, audit details, media URL availability checks, and attachment preview optimization. | Demonstrates engineering completeness and product experience. |
| P2 | Mobile adaptation, complex reward rules, multi-model routing, sampling strategy, and offline cache. | Bonus items to add depending on remaining time. |

8.3 Conclusion

The focus of this project is not merely to pile up features, but to make three complex capabilities solid: configurable dynamic forms, traceable workflows, and a production-ready AI quality-inspection Agent. During development, the team should always use the end-to-end closed loop as the anchor, produce a demonstrable version each week, and finally deliver a complete package including source code, deployment environment, API documentation, demo video, and key design documents.

Project Implementation Plan - Internal Implementation Version